## 1. Human Resources
Resource Name | Role | Department | Allocation % | Hourly Rate (VND)
Nguyen Van A | Project Manager | PMO | 100% | 250
Tran Thi B | Business Analyst | Product | 100% | 180
Le Van C | Backend Developer | Engineering | 100% | 220
Hoang Van D | Frontend Developer | Engineering | 100% | 200
Pham Thi E | QC/Tester | QA | 50% | 150

## 2. Project Timeline & Tasks
Resource Name | Role | Department | Allocation % | Hourly Rate (VND)
Nguyen Van A | Project Manager | PMO | 100% | 250
Tran Thi B | Business Analyst | Product | 100% | 180
Le Van C | Backend Developer | Engineering | 100% | 220
Hoang Van D | Frontend Developer | Engineering | 100% | 200
Pham Thi E | QC/Tester | QA | 50% | 150

## 3. Infrastructure & Budget
Category | Item Description | Provider | Monthly Cost (VND) | Total (7 Months)
Cloud Hosting | AWS EC2 / RDS / S3 | Amazon Web Services | 5,000,000 | 35,000,000
AI Tokens | LLM API (Gemini/OpenAI) | Google/OpenAI | 2,500,000 | 17,500,000
Maps API | Google Maps Platform | Google | 3,000,000 | 21,000,000
Workspaces | GitHub/Slack/Jira | Various | 1,500,000 | 10,500,000